## Sprint 5 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 5 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
Remaining work to be done.
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
5.1 | PB5.1 | Sprint Planning Meeting | Team | Not Start | 4 | 0 | 4
5.2 | PB5.2 | Create Sprint Backlog | Team | Not Start | 4 | 0 | 4
5.3 | PB5.3 | Create Test Plan document | Team | Not Start | 4 | 0 | 4
5.4 | PB5.4 | Design user interface | Team | Not Start | 0 | 0 | 0
5.4.1 | PB5.4.1 | Design user interface “Login Admin” | Team | Not Start | 4 | 0 | 4
5.4.2 | PB5.4.2 | Design user interface “Update Admin” | Team | Not Start | 4 | 0 | 4
5.5 | PB5.5 | Design Test Case | Team | Not Start |  |  | 0
5.5.1 | PB5.5.1 | Design Test Case “Login Admin” | Team | Not Start | 4 | 0 | 4
5.5.2 | PB5.5.2 | Design Test Case “Update Admin” | Team | Not Start | 4 | 0 | 4
5.6 | PB5.6 | Coding | Team | Not Start | 0 | 0 | 0
5.6.1 | PB5.6.1 | Coding “Login Admin” | Team | Not Start | 20 | 0 | 20
5.6.2 | PB5.6.2 | Coding “Update Admin” | Team | Not Start | 20 | 0 | 20
5.7 | PB5.7 | Testing | Team | Not Start | 0 | 0 | 0
5.7.1 | PB5.7.1 | Testing “Login Admin” | Team | Not Start | 4 | 0 | 4
5.7.2 | PB5.7.2 | Testing “Update Admin” | Team | Not Start | 4 | 0 | 4
5.8 | PB5.8 | Fix Bug | Team | Not Start | 0 | 0 | 0
5.8.1 | PB5.8.1 | Fix Bug “Login Admin” | Team | Not Start | 6 | 0 | 0
5.8.2 | PB5.8.2 | Fix Bug “Update Admin” | Team | Not Start | 6 | 0 | 0
|  |  |  | Total | 88 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down |  |  |  | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88
|  |  |  | Burn up |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B7: jan samuelsson: 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: jan samuelsson: Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.
Note on H7: jan samuelsson: Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.

## Sprint 4 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 4 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
Remaining work to be done.
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
4.1 | PB4.1 | Sprint Planning Meeting | Team | Done | 6 | 6 | 0 | 4 | 4
4.2 | PB4.2 | Create Sprint Backlog | Team | Done | 4 | 4 | 0 |  | 4
4.3 | PB4.3 | Create Test Plan document | Team | Done | 4 | 4 | 0 |  |  | 4
4.4 | PB4.3 | Create Test Case | Team | Done | 6 | 6 | 0 |  |  | 4 | 2
4.4 | PB4.4 | Coding ChatBot | Team | To Do | 50 | 50 | 0
4.5 | PB4.5 | Testing ChatBot | Team | To Do | 10 | 10 | 0
4.6 | PB4.6 | Fix Bug ChatBot | Team | Not Start | 20 | 20 | 0
|  |  |  | Total | 100 | 100 | 0 | 4 | 8 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down |  |  |  | 96 | 88 | 80 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78
|  |  |  | Burn up |  |  |  | 4 | 12 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
Note on B7: jan samuelsson: 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: jan samuelsson: Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.
Note on H7: jan samuelsson: Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.

## Main
Scrum Project |  |  | Product Status | In progress
Sponsor
Product
Active versions
|  |  | Product Owner | Le Anh Khoa
Team |  |  | Project Champion
Scrum Master | Hoang Quang Dat |  | Other Stakeholders
Developers | Nguyen Dang Tuong Lam
Le Anh Khoa
Nguyen Thanh Quoc
Projects | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Remarks
1 | Requirement Analysis | 23/8/2021 | 30/8/2021 | In Progress |  | Spr. 1.1
2 | Design | 2021-01-09 | 30/9/201 | In Progress |  | Spr. 1.2
3 | Code |  |  |  |  | Spr. 1.3
4 | Testing |  |  |  |  | Spr. 1.4
5 | Delivery |  |  |  |  | Spr. 1.5

## Product Backlog
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Visit the homepage of the website | User | Access to website | Users need to access the website | By searching the keyword COVID-19 iConsultant |  | 0 |  |  |  | 0 | 0
PB02 | Visit the page "Q&A Phòng ngừa COVID-19" | User | See available Q&A on COVID-19 prevention | Users can view available Q&A to improve knowledge about COVID-19 prevention | Questions and answers answer questions about prevention of COVID-19 for readers. |  | 3 |  |  |  | 2 | 40
PB03 | Visit the page "Tin tức" | User | See the latest and accurate news | Provide fresh information and access to accurate information sources. | News related to COVID-19 and compiled based on sources of government agencies and WHO. |  | 4 |  |  |  | 2 | 30
PB04 | Visit the page "Số liệu về COVID-19 và Vắc-xin COVID-19" | User | Users can see the statistics of COVID-19 and Vaccines of Vietnam | Provide data on the number of cases, recoveries and deaths of COVID-19. Provide data on the COVID-19 Vaccine | The graph shows the evolution of COVID-19 and the COVID-19 vaccine. The data table provides visual data on COVID-19 and Vaccine. |  | 2 |  |  |  | 1 | 60
PB05 | Bot chat | User | Communicate with bot chat | Ask questions related to COVID-19 for Chatbot to give answers. | Chatbot can answer questions related to COVID-19 or give answers corresponding to the question if the question is not already in the system. There is also an answer to the exception questions. |  | 1 |  |  |  | 3,4 | 80
PB06 | Login | Admin | Login into the website with "user name" and "password" have website management email | Manage website content. | Log in with an account with the website management email. Login requires the correct password and username.
Note on M7: jan samuelsson: Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.

## Sprint 1 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
Remaining work to be done.
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
1.1 | PB1.1 | Sprint Planning Meeting | Team | Done | 4 | 4 | 0 | 2 | 2
1.2 | PB1.2 | Create Sprint Backlog | Team | Done | 4 | 4 | 0 |  | 2 | 2
1.3 | PB1.3 | Create Test Plan document | Team | Done | 6 | 6 | 0 |  |  | 6
1.4 | PB1.4 | Design user interface Page “Số liệu COVID-19” | Team | Done | 8 | 8 | 0 |  |  |  | 4 | 4
1.5 | PB1.5 | Design Data Page “Số liệu COVID-19” | Team | Done | 8 | 8 | 0 |  |  |  |  | 4 | 4
1.6 | PB1.6 | Design Test Case Page “Số liệu COVID-19” | Team | Done | 8 | 8 | 0 | [5 empty] | 4 | 4
1.7 | PB1.7 | Coding Page “Số liệu COVID-19” | Team | To Do | 32 | 0 | 32
1.8 | PB1.8 | Testing Page “Số liệu COVID-19” | Team | To Do | 8 | 0 | 8
1.9 | PB1.9 | Fix Bug Page “Số liệu COVID-19” | Team | Not Start | 16 | 0 | 16
|  |  |  | Total | 94 | 38 | 56 | 2 | 4 | 8 | 4 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down |  |  |  | 92 | 88 | 80 | 76 | 68 | 60 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56
|  |  |  | Burn up |  |  |  | 2 | 6 | 14 | 18 | 26 | 34 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38
Note on B7: jan samuelsson: 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: jan samuelsson: Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.
Note on H7: jan samuelsson: Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 2 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
Remaining work to be done.
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
2.1 | PB2.1 | Sprint Planning Meeting | Team | Done | 4 | 4 | 0 | 4
2.2 | PB2.2 | Create Sprint Backlog | Team | Done | 4 | 4 | 0 | 4
2.3 | PB2.3 | Create Test Plan document | Team | Done | 6 | 6 | 0 |  | 6
2.4 | PB2.4 | Design user interface | Team | Done | 0 | 0 | 0
2.4.1 | PB2.4.1 | Design user interface “Hỏi đáp phòng chống COVID-19” | Team | Done | 6 | 6 | 0 |  | 2 | 4
2.4.2 | PB2.4.2 | Design user interface Page “Tin tức COVID-19” | Team | Done | 6 | 6 | 0 |  |  | 4 | 2
2.5 | PB2.5 | Design Data | Team | Done
2.5.1 | PB2.5.1 | Design Data “Hỏi đáp phòng chống COVID-19” | Team | Done | 6 | 6 | 0 |  |  |  | 6
2.5.2 | PB2.5.2 | Design Data “Tin tức COVID-19” | Team | Done | 6 | 6 | 0 |  |  |  |  | 6
2.6 | PB2.6 | Design Test Case | Team | Done | 0 | 0 | 0
2.6.1 | PB2.6.1 | Design Test Case Page “Hỏi đáp phòng chống COVID-19” | Team | Done | 4 | 4 | 0 |  |  |  |  | 2 | 2
2.6.2 | PB2.6.2 | Design Test Case Page “Tin tức COVID-19” | Team | Done | 4 | 4 | 0 | [5 empty] | 4
2.7 | PB2.7 | Coding | Team | To Do
2.7.1 | PB2.7.1 | Coding Page “Hỏi đáp phòng chống COVID-19” | Team | To Do | 20 | 0 | 20
2.7.2 | PB2.7.2 | Coding Page “Tin tức COVID-19” | Team | To Do | 20 | 0 | 20
2.8 | PB2.8 | Testing | Team | To Do |  |  | 0
2.8.1 | PB2.8.1 | Testing Page “Hỏi đáp phòng chống COVID-19” | Team | To Do | 4 | 0 | 4
2.8.2 | PB2.8.2 | Testing Page “Tin tức COVID-19” | Team | To Do | 4 | 0 | 4
2.9 | PB2.9 | Fix Bug | Team | Not Start |  |  | 0
2.9.1 | PB2.9.1 | Fix Bug Page “Hỏi đáp phòng chống COVID-19” | Team | Not Start | 8 | 0 | 8
2.9.2 | PB2.9.2 | Fix Bug Page “Tin tức COVID-19” | Team | Not Start | 8 | 0 | 8
|  |  |  | Total | 110 | 46 | 64 | 8 | 8 | 8 | 8 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down |  |  |  | 102 | 94 | 86 | 78 | 70 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64
|  |  |  | Burn up |  |  |  | 8 | 16 | 24 | 32 | 40 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46
Note on B7: jan samuelsson: 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: jan samuelsson: Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.
Note on H7: jan samuelsson: Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.

## Sprint 2 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 3 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
Remaining work to be done.
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
3.1 | PB3.1 | Sprint Planning Meeting | Team | Done | 4 | 4 | 0 | 4
3.2 | PB3.2 | Create Sprint Backlog | Team | Done | 4 | 4 | 0 | 4
3.3 | PB3.3 | Create Test Plan document | Team | Done | 6 | 6 | 0 |  | 6
3.4 | PB3.4 | Sprint Planning Meeting | Team | Done | 4 | 4 | 0 |  | 2 | 2
3.5 | PB3.5 | Create Sprint Backlog | Team | Done | 6 | 6 | 0 |  |  | 6
3.6 | PB3.6 | Create Test Plan document | Team | Done | 6 | 6 | 0 |  |  |  | 6
3.7 | PB3.7 | Design user interface ChatBot | Team | Done | 16 | 16 | 0 |  |  |  | 2 | 8 | 6
3.8 | PB3.8 | Design Test Case ChatBot | Team | Done | 16 | 16 | 0 | [5 empty] | 2 | 6 | 8
3.9 | PB3.9 | Coding ChatBot | Team | Done | 40 | 40 | 0 | [8 empty] | 8 | 8 | 4 | 8 | 4 | 8
|  |  |  | Total | 102 | 102 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 8 | 8 | 8 | 4 | 8 | 4 | 8
|  |  |  | Burn down |  |  |  | 94 | 86 | 78 | 70 | 62 | 54 | 48 | 40 | 32 | 24 | 20 | 12 | 8 | 0
|  |  |  | Burn up |  |  |  | 8 | 16 | 24 | 32 | 40 | 48 | 54 | 62 | 70 | 78 | 82 | 90 | 94 | 102
Note on B7: jan samuelsson: 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: jan samuelsson: Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.
Note on H7: jan samuelsson: Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.

## Sprint 3 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Impediment
Impediments | [5 empty] | In charge of removing the impediment | Not started Ongoing Done
|  |  | Date | [5 empty] | Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On

## Retrospective
In the retrospecitve meeting after each sprint you will identify/find many things to improve. That does not mean that you will do all the changes in the next sprint. Usually you do changes step by step. E.g. 1-3 changes in one sprint. Not more than that. So sometimes you find an improvement in one sprint and then in a much later sprint you will actually do the change.
Retrospective Log
Found in Sprint # | Impl. In Sprint # |  | Responsible for doing the improvement
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms